## Pacing Summary
Turkish Airlines Video Campaign - Pacing & Delivery Report
Data snapshot: June 19 - July 1 ¦ Flight: June 19 - July 15 ¦ Rate: $30.00 CPM
1. Campaign Parameters
Metric | Value
Impression goal | 3062654
Budget | 91880
Implied rate (CPM) | 30
Flight start | 2026-06-19
Flight end | 2026-07-15
Flight length (days) | 27
2. Required Daily Pace (to hit goal on time)
Calculation | Value
Impression goal | 3062654
Flight length (days) | 27
Required impressions / day
3. Actual Delivery vs Plan (through July 1)
Checkpoint | Value | Read
Total delivered (impressions) | 478528
Total revenue delivered | 14356
Days delivered | 13
Avg impressions / day (actual) | 36810 | Run rate
Time elapsed (% of flight) | 48.15% | -
Goal delivered (%) | 15.62% | Far behind
Actual vs required pace | 32.45% | Running at ~1/3 speed
Budget spent (%) | 15.62% | CPM holding at $30

## Daily Delivery
Day-wise Delivery (June 19 - July 1)
Date | Ad server impressions | Revenue
2026-06-19 | 15646 | 469
2026-06-20 | 29797 | 894
2026-06-21 | 29966 | 899
2026-06-22 | 40618 | 1219
2026-06-23 | 26209 | 786
2026-06-24 | 59556 | 1787
2026-06-25 | 63998 | 1920
2026-06-26 | 38874 | 1166
2026-06-27 | 30729 | 922
2026-06-28 | 31541 | 946
2026-06-29 | 37298 | 1119
2026-06-30 | 48568 | 1457
2026-07-01 | 25728 | 772
Grand Total

## Projection & Catch-up
Projection & Catch-up Scenarios
4. If Performance Continues As-Is
Metric | Value
Current run rate (imp/day) | 36810
Projected total by July 15 (27 days) | 993870
Projected % of goal | 32.45%
Shortfall vs goal (impressions) | 2068784
Days to fully deliver at current pace | 83.2017
Projected actual finish date | ~September 9
5. What's Needed to Finish On Time (by July 15)
Metric | Value
Goal | 3062654
Delivered so far | 478528
Remaining impressions | 2584126
Remaining days (July 2-15) | 14
Required imp/day to finish on time | 184580.4286
Multiple of current pace | 5.0144
Best single day so far (June 25) | 63998
Best day vs required catch-up pace | 34.67%

## Line Item Breakdown
Delivery by Format / Line Item
Format | Line item | Ad server impressions | Revenue | % of total
Bytes | 12213418 Vertical Video - ROS - Widget | 297608 | 8928 | 65.73%
Bytes | 12238249 Vertical Video - ROS - Widget v2 | 64921 | 1948 | 14.34%
Bytes | 12232491 Vertical Video ROS - In Stream only | 4592 | 138 | 1.014%
Bytes | 12212858 Vertical Video ROS - In content only | 1062 | 32 | 0.2345%
Bytes | 12238447 Vertical Video - ROS - In content v3 | 816 | 24 | 0.1802%
Bytes | 12212859 Vertical Video - Channel targeted - Incontent only | 361 | 11 | 0.07973%
Bytes | 12212857 Vertical Video - Mnet + Personas - Incontent only | 241 | 7 | 0.05322%
Pre Roll | 12212826 Standard Pre-roll ROS | 82888 | 2487 | 18.31%
Pre Roll | 12212854 Standard Pre-roll - Channel targeted | 187 | 6 | 0.0413%
Pre Roll | 11768253 Standard Pre-roll - Mnet + Personas | 124 | 4 | 0.02739%
Grand Total

## Recommendations
Recommendations & Scenarios
# | Recommendation | Rationale
1 | Loosen / lift targeted line items | Channel-targeted + Mnet+Personas delivering ~0.1%; reallocate to ROS Widget.
2 | Shift weight to top 3 performers | Widget, Widget v2, Pre-roll ROS drive ~98% of delivery; uncap freq/geo.
3 | Reset goal expectations | Hitting 3.06M by July 15 needs ~5x best-ever pace; not achievable as-is.
Two Paths to Present to Client
Path | Action | Outcome
A - Extend flight | Keep $30 CPM & current pace | Full delivery ~early-mid September
B - Rescope goal | Right-size goal to flight | ~1.0-1.3M imps by July 15 (~$30-39K spend)